# CCoT Action Planning Matrix

Tool Overview: Use this fillable template during team action-planning sessions to break CCoT priorities down into manageable, accountable steps using the Plan-Do-Study-Act framework.

### Activity & Goal Overview

| Selected Activity / Goal | Outside Agency Roadshow for Educators |
| --- | --- |
| Target Completion Date |  |

### Action Planning & Implementation Matrix (PLAN / DO)

Identify the specific actionable items needed for the team to complete the selected activity and assign responsible team members.

| Action Steps (Activity Planning — PLAN / DO) | Person(s) Responsible (Which team member(s) lead this item?) | Target Date | Status |
| --- | --- | --- | --- |
| Step 1: Make a list of key local agencies that support transition. | CCoT Core Team during September meeting |  | Pending Complete |
| Step 2: Reach out to agency reps to invite them to present or contribute materials, providing them with goals and audience needs. | Each subcommittee member assigned 2–3 agencies based on October finalized list |  | Pending Complete |
| Step 3: Outline educator learning goals (who agencies are, when to involve them, referral info) and build slide/handout template. | CCoT Workgroup |  | Pending Complete |
| Step 4: Set date, time, and format with each county school (reserve space, set up Zoom, etc.), confirm participants, and promote within schools. | CCoT Workgroup leader, school district reps |  | Pending Complete |
| Step 5: Facilitate session, provide educator-friendly materials, and encourage future connections/questions. | Assigned facilitators |  | Pending Complete |
| Step 6: Send thank you notes, share follow-up materials, and review feedback data to improve future sessions | CCoT Facilitator leads discussion |  | Pending Complete |

### Progress Monitoring & Continuous Improvement (STUDY / ACT)

Evaluate how the activity went using data metrics, summarize accomplishments, and determine your next steps.

| Phase | Evaluation & Reflection Questions | Team Notes & Summary |
| --- | --- | --- |
| Progress Monitoring (STUDY) | How will the action steps be evaluated? What data metrics, survey feedback, attendance numbers, or outcome benchmarks will you review? | - Agency List: Final list reviewed and approved at October CCoT meeting. - Participation Tracking: Track confirmed agency reps via shared spreadsheet. - Content Review: Review slide/handout template during December CCoT meeting and shared documents. - Logistics Schedule: Schedule with 80% of schools by February; confirm all logistics 2 weeks prior. - Attendance & Feedback: Collect attendance numbers and short feedback survey. - Review: Review and discuss feedback data at next CCoT meeting after each event. |
| Progress & Accomplishments Summary (ACT) | Summarize findings and identify next steps: What worked well? What do findings show? What changes or next steps will the team take moving forward? |  |

The Transition Improvement Grant (TIG) (CFDA# 84.027A) acknowledges the support of the Wisconsin Department of Public Instruction in the development of this material and for the continued support of this federally funded grant program. There are no copyright restrictions on this document; however, please credit the Wisconsin DPI and support of federal funds when copying all or part of this material.